## Sprint 0
Project | FoodMind Application
Student | Chen Chen
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Attend Project Briefing | 2 | 2
|  | Review requirements; identify profile/preference workstream | 2.5 | 2.5
|  | Team work allocation | 2 | 2
Total
2026-07-24 | Friday | Draft proposal | 2 | 2
|  | Android account/preference baseline study | 2.5 | 2.5
|  | Architecture review | 2 | 2
Total
2026-07-25 | Saturday | Draft use cases | 2 | 2
|  | Map profile/preference requirements | 2.5 | 2.5
|  | UI pattern research | 2 | 2
Total
2026-07-26 | Sunday | Consolidate proposal | 2 | 2
|  | Review architecture | 2.5 | 2.5
|  | Prepare proposal slides | 2 | 2
Total
2026-07-27 | Monday | Support Proposal Presentation | 2 | 2
|  | Rehearse | 2.5 | 2.5
|  | Record feedback | 2 | 2
Total
2026-07-28 | Tuesday | Android project setup | 2.5 | 2.5
|  | Account feature skeleton | 2 | 2
|  | Navigation framework | 2 | 2
Total
2026-07-29 | Wednesday | Review user_preference API contract | 2 | 2
|  | Preference taxonomy mapping (cuisine/dietary/allergen) | 2.5 | 2.5
|  | Compose UI skeleton | 2 | 2
Total
2026-07-30 | Thursday | Advisor Meeting 1 (support) | 1 | 1
|  | Profile screen design | 2.5 | 2.5
|  | Preference screen design | 3 | 3
Total
2026-07-31 | Friday | Profile UI states design | 2 | 2
|  | Preference chip design | 2.5 | 2.5
|  | Accessibility review | 2 | 2
Total
2026-08-01 | Saturday | Android auth (LoginActivity) integration | 2.5 | 2.5
|  | Token/session handling (KeystoreSessionTokenStore) | 2 | 2
|  | ProfileActivity layout | 2 | 2
Total
2026-08-02 | Sunday | Preference form fields mapping | 2 | 2
|  | user_dietary_tag / user_allergen UI | 2.5 | 2.5
|  | Design review | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Chen Chen
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | ProfileActivity implementation | 3 | 3
|  | Preference screen layout (Compose) | 2.5 | 2.5
|  | Strings/styles/dimens/colours | 2 | 2
Total
2026-08-04 | Tuesday | FoodPreferenceActivity data binding | 3 | 3
|  | Liked/avoided cuisine mutual exclusion | 2.5 | 2.5
|  | Spice slider + live summary | 2 | 2
Total
2026-08-05 | Wednesday | Confirm project theme and problem scope | 3 | 3.5
|  | Review requirements and profile/preference workstream | 3 | 4
Total
2026-08-06 | Thursday | Confirm team division for Manage Profile and Food Preference | 3.5 | 3
|  | Map profile/preference functions, UI states and integration | 3 | 4
Total
2026-08-07 | Friday | Set up local repositories and review architecture | 4 | 7
Total
2026-08-08 | Saturday | Analyse Android UI components, theme and navigation | 3.5 | 4.5
|  | Study ProfileActivity structure and reusable UI patterns | 3 | 4
Total
2026-08-09 | Sunday | Design Android food-preference screen (UI style) | 2.5 | 3
|  | Define liked/avoided cuisine, meal type, dietary tag, spice level | 2.5 | 3.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Chen Chen
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Implement activity_food_preference.xml (toolbar/cards/chips) | 4 | 3.5
|  | Add FoodMind strings, styles, dimensions, colours | 2 | 3
Total
2026-08-11 | Tuesday | Implement FoodPreferenceActivity dynamic chips + mutual exclusion | 3 | 3.5
|  | Bind meal/dietary choices, spice slider, live summary | 2 | 3
Total
2026-08-12 | Wednesday | Design-time preference preview and English resource overrides | 2 | 3
|  | Resolve Android Studio preview/theme issues and check build | 2.5 | 3.5
Total
2026-08-13 | Thursday | Analyse official Compose Profile/Preferences screens | 4 | 5
Total
2026-08-14 | Friday | Wire preference save to Backend user_preference API | 3 | 3
|  | user_cuisine_preference / user_dietary_tag mapping | 2 | 2.5
|  | Preference aggregate contract check | 1.5 | 2
Total
2026-08-15 | Saturday | Test Web sign-in, Profile display and editing | 2.5 | 3.5
|  | Test Web Preferences loading/editing/saving/refresh | 2 | 3
Total
2026-08-16 | Sunday | Test Android Profile display/editing and Preferences navigation (emulator) | 2 | 2.5
|  | Test Android Preference loading/selection/saving/persisted values | 2.5 | 3
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Chen Chen
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Repeat assigned Web and Android user flows | 3 | 3.5
|  | Check validation, loading/error feedback, cross-client consistency | 1.5 | 3.5
Total
2026-08-18 | Tuesday | Run final Web/Android demo test for Profile and Food Preference | 3.5 | 4
|  | Record test results and prepare screenshots/code notes | 1.5 | 2.5
Total
2026-08-19 | Wednesday | DevSecOps Presentation (support) | 1 | 1
|  | Review preference security checks | 3 | 3
|  | Apply report feedback | 2.5 | 2.5
Total
2026-08-20 | Thursday | Rehearse Profile/Food Preference demo | 3 | 3
|  | Organise submission evidence | 2 | 2
|  | Prepare fallbacks | 1.5 | 1.5
Total
2026-08-21 | Friday | AD Project Presentation (account/preference) | 2 | 2
|  | Final preflight | 2 | 2
|  | Complete report | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm