## Sprint 0
Project | FoodMind Application
Student | Chen Yaqi
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Attend Project Briefing | 2 | 2
|  | Define Backend/Web ownership and scope | 2.5 | 2.5
|  | Draft team work allocation | 2 | 2
Total
2026-07-24 | Friday | Review AD proposal baseline | 2 | 2
|  | Map repository boundaries (backend/web/intelligence/ml/infra) | 2.5 | 2.5
|  | Draft architecture boundaries | 2 | 2
Total
2026-07-25 | Saturday | Define backend bounded contexts | 2.5 | 2.5
|  | Draft Flyway schema plan | 2 | 2
|  | Outline /api/v1 OpenAPI v0 | 2 | 2
Total
2026-07-26 | Sunday | Consolidate proposal slides | 2 | 2
|  | Review architecture | 2.5 | 2.5
|  | Prepare proposal presentation | 2 | 2
Total
2026-07-27 | Monday | Attend Proposal Presentation | 2 | 2
|  | Create GitHub repos | 1.5 | 1.5
|  | Freeze public OpenAPI skeleton | 3 | 3
Total
2026-07-28 | Tuesday | Plan product priorities and team work allocation | 2 | 2
|  | Build responsive Web UX prototype and refocus recommendation flow | 3 | 3
|  | Align Android/backend/intelligence/ML recommendation-first contracts | 2 | 2
|  | Update architecture and status docs | 1.5 | 1.5
|  | Complete backend DB schema and hand-off | 1.5 | 1.5
Total
2026-07-29 | Wednesday | Backend foundation: PostgreSQL/Flyway runtime and test/CI setup | 2.5 | 2.5
|  | Common API contracts: errors, pagination, validation, correlation IDs | 1.5 | 1.5
|  | Authentication: JWT issuance, refresh rotation, revocation | 1.5 | 1.5
|  | User profile and preferences aggregate | 1.5 | 1.5
|  | Catalogue read ports, fixtures, API reference | 1.5 | 1.5
|  | Food records: CRUD, ownership, soft-deletion | 1.5 | 1.5
Total
2026-07-30 | Thursday | Recommendation/groups/search/Want to Try permission-safe flows | 2.5 | 2.5
|  | Cooking and Chat Agent orchestration and grounded snapshots | 2.5 | 2.5
|  | Dashboard, weekly recap, media uploads, storage config | 2.5 | 2.5
|  | Backend docs, contracts, security tests, fixtures | 2 | 2
Total
2026-07-31 | Friday | Implement Web client API integration | 4 | 4
|  | Add Web operations and security docs | 2 | 2
|  | Verify frontend contracts and delivery readiness | 2 | 2
|  | Review and document Web client changes | 1.5 | 1.5
Total
2026-08-01 | Saturday | Wire Web HomeRoutes/RecordRoutes to backend API | 3 | 3
|  | Add shared API client and query-keys | 2.5 | 2.5
|  | Coverage gate for generated schema | 1.5 | 1.5
Total
2026-08-02 | Sunday | Review Cooking plan v2 hand-off | 2 | 2
|  | Document UI design flows | 3 | 3
|  | Align Cooking Agent adaptation with API docs | 1.5 | 1.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Chen Yaqi
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | Design Recommendation Agent integration architecture | 3 | 3
|  | Document recommendation model/feature/evaluation guidance | 2 | 2
|  | Update Recommendation Agent delivery decisions | 1.5 | 1.5
Total
2026-08-04 | Tuesday | Compile backend architecture and implementation status | 3 | 3
|  | Compile Intelligence service overview and integration notes | 1.5 | 1.5
|  | Organise project reference files for hand-off | 2 | 2
Total
2026-08-05 | Wednesday | Freeze Backend /api/v1 OpenAPI for client consumption | 3 | 3
|  | Add AuthController refresh/CSRF contract | 2 | 2
|  | OpenAPI examples and consumer snapshot | 1.5 | 1.5
Total
2026-08-06 | Thursday | Integrate Cooking async-task API contract across clients | 3.5 | 3.5
|  | Wire Web Cooking async-task routes and types | 3.5 | 3.5
|  | Review cross-client Cooking delivery alignment | 2 | 2
Total
2026-08-07 | Friday | Backend recipe catalogue read ports | 2.5 | 2.5
|  | Group membership/ownership permission tests | 2.5 | 2.5
|  | Search/Explore permission-scoped SQL functions | 2 | 2
Total
2026-08-08 | Saturday | Web GroupRoutes and group feed | 3 | 3
|  | Web ExploreRoutes permission-safe feed | 2.5 | 2.5
|  | States: loading/empty/error/forbidden | 1.5 | 1.5
Total
2026-08-09 | Sunday | Recommendation fallback selector + reason templates | 3 | 3
|  | Feedback event matrix validation | 2 | 2
|  | Idempotency record for recommendation | 1.5 | 1.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Chen Yaqi
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Add food-record recommendation candidate flow (Backend) | 3.5 | 3.5
|  | RecommendationAgentHttpAdapter + contract validation | 2 | 2
|  | ChatAgentHttpAdapter + DelegationTokenIssuer | 2 | 2
|  | Align source-neutral candidate contracts | 2 | 2
Total
2026-08-11 | Tuesday | Standardise Backend P0 recommendation response contract in OpenAPI | 3.5 | 3.5
|  | Add RecommendationResponseContractTest | 2 | 2
|  | Verify recommendation API delivery readiness | 1 | 1
Total
2026-08-12 | Wednesday | Android/Web backend parity and real-stack E2E gates | 2.5 | 2.5
|  | Enable local Backend/Intelligence stack (agent ports, auth) | 2.5 | 2.5
|  | Deliver grounded Chat exploration and source scoping | 2 | 2
|  | One-command local infra stack and CI docs | 2.5 | 2.5
Total
2026-08-13 | Thursday | Point Android debug/release API config to deployed backend | 2 | 2
|  | Extend Chat search/explore fields and read-only answers | 2.5 | 2.5
|  | Harden Backend/Intelligence/Web/Infra CI checks | 2.5 | 2.5
|  | Review cross-repo deployment readiness | 2.5 | 2.5
Total
2026-08-14 | Friday | Restore Android/Web Chatbot integration parity | 2.5 | 2.5
|  | Require verifiable DeepSeek generation (server config) | 2 | 2
|  | Bound DeepSeek sampling via runtime config | 2 | 2
Total
2026-08-15 | Saturday | Recommendation diversity/rejection/exclusion (Backend filter pipeline) | 2.5 | 2.5
|  | Serve collaborative signals via ML/Intelligence/Backend wiring | 2.5 | 2.5
|  | Recommendation explanations and refresh flows (API contract) | 2.5 | 2.5
|  | Restrict Chatbot answers to FoodMind scope | 2 | 2
Total
2026-08-16 | Sunday | OneMap walking-route support (Backend + Web) | 3.5 | 3.5
|  | Configure OneMap secret and location permissions | 2 | 2
|  | Integrate place-navigation experience | 2 | 2
|  | Document OneMap advanced extension | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Chen Yaqi
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Prepare Backend continuous-delivery pipeline | 3 | 3
|  | Build Infra DevSecOps pipeline stages | 3 | 3
|  | Correct DevSecOps evidence and delivery scripts | 2.5 | 2.5
|  | Review cross-repo CI/CD readiness | 1 | 1
Total
2026-08-18 | Tuesday | Test Backend CD pipeline (Netty dependency correction) | 3.5 | 3.5
|  | Validate Infra DevSecOps pipeline stages | 3 | 3
|  | Document CI/CD test results | 2 | 2
|  | Review pipeline failures | 1 | 1
Total
2026-08-19 | Wednesday | Run and verify Backend continuous-delivery pipeline | 3 | 3
|  | DevSecOps Presentation (Infra owner) | 1.5 | 1.5
|  | Test Infra DevSecOps pipeline and deployment validation | 2.5 | 2.5
|  | Review CI/CD results and follow-ups | 1 | 1
Total
2026-08-20 | Thursday | Rehearse Backend/Web final demo | 3 | 3
|  | Organise submission and evidence | 2.5 | 2.5
|  | Prepare fallbacks for demo | 1.5 | 1.5
Total
2026-08-21 | Friday | AD Project Presentation (Backend/Web/Infra lead) | 2 | 2
|  | Run final preflight checks | 2.5 | 2.5
|  | Complete contribution report | 2 | 2
Total
2026-08-20 | Thursday | Normalise unsupported media uploads across Android and Web and improve image removal behaviour | 3.5 | 3.5
|  | Enrich Backend Chat reference grounding snippets for more useful source context | 2.5 | 2.5
|  | Add Intelligence support for exploring recently recorded places through Chat | 2 | 2
|  | Review cross-client media and Chat contract alignment and verify delivery readiness | 1.5 | 1.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm