## Sprint 0
Project | FoodMind Application
Student | Huang Qijun
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Project Briefing | 1.5 | 1.5
|  | Review Cooking Feature Brief | 2.5 | 2.5
|  | Define Recipe Assistant Scope | 3 | 2.5
Total
2026-07-24 | Friday | Refine Cooking Requirements | 2 | 2
|  | Define Recipe Generation MVP | 3 | 4
|  | Review Cooking Acceptance Criteria | 2 | 2
Total
2026-07-25 | Saturday | Analyse Home-Cooking Users | 2.5 | 2.5
|  | Draft Cooking Use Cases | 2.5 | 2.5
|  | Map Cooking System Roles | 2 | 2
Total
2026-07-26 | Sunday | Consolidate Cooking Proposal | 2.5 | 2.5
|  | Review Cooking Architecture | 2.5 | 2.5
|  | Prepare Cooking Proposal Slides | 2 | 2
Total
2026-07-27 | Monday | Present Cooking Feature Proposal | 2 | 2
|  | Rehearse Cooking Flow | 3 | 3
|  | Record Cooking Feedback | 2.5 | 2.5
Total
2026-07-28 | Tuesday | Map Recipe Creation Flow | 3 | 3
|  | Map Recipe Import Flow | 2 | 2
|  | Map Meal Planning Flow | 2 | 1.5
Total
2026-07-29 | Wednesday | Review Cooking API Contract | 2 | 1.5
|  | Map Recipe Form Fields | 2.5 | 2.5
|  | Define Recipe Access Rules | 2.5 | 3
Total
2026-07-30 | Thursday | Advisor Meeting 1 (present Cooking) | 1.5 | 1.5
|  | Confirm Cooking Task Split | 3.5 | 3.5
|  | Update Cooking Design Plan | 2 | 2
Total
2026-07-31 | Friday | Design Recipe Navigation | 2 | 2
|  | Design Ingredient Picker | 2 | 2
|  | Review Cooking Accessibility | 2 | 2.5
Total
2026-08-01 | Saturday | Design Recipe Detail Form | 2 | 2
|  | Define Serving Adjustment Rules | 2 | 2
|  | Design Recipe Visibility | 2 | 2
Total
2026-08-02 | Sunday | Design Import Review Screen | 2.5 | 2.5
|  | Define Ingredient Note Rules | 2 | 2
|  | Design Recipe Photo Flow | 2.5 | 2.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Huang Qijun
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | Design Recipe Collection | 2 | 2
|  | Define Recipe Context | 2 | 2
|  | Define Recipe Return Flow | 2 | 2
Total
2026-08-04 | Tuesday | Prototype Web Cooking Flow | 2.5 | 2.5
|  | Prototype Android Cooking Flow | 2 | 2
|  | Check Cross-Client Cooking Parity | 1.5 | 1.5
Total
2026-08-05 | Wednesday | Design Recipe Error States | 2 | 2
|  | Plan Recipe Draft Retention | 1.5 | 1.5
|  | Prevent Duplicate Imports | 2.5 | 2.5
Total
2026-08-06 | Thursday | Run Cooking Usability Check | 2 | 2
|  | Refine Recipe Form Copy | 2.5 | 2
|  | Finalize Cooking Wireframes | 2 | 2
Total
2026-08-07 | Friday | Advisor Meeting 2 (present Cooking Design) | 1.5 | 1.5
|  | Present Cooking Design | 2.5 | 2.5
|  | Record Cooking Feedback | 3 | 2.5
Total
2026-08-08 | Saturday | Set Up Web Cooking Forms | 1.5 | 1.5
|  | Build Ingredient Picker | 2.5 | 2.5
|  | Add Cooking Navigation | 2 | 2
Total
2026-08-09 | Sunday | Build Recipe Form | 2 | 2
|  | Add Recipe Validation | 3 | 3
|  | Map Serving Adjustment | 2 | 1
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Huang Qijun
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Build Recipe Import Screen | 1.5 | 1.5
|  | Add Recipe Photo Upload | 3.5 | 3.5
|  | Handle Recipe Visibility | 2 | 2
Total
2026-08-11 | Tuesday | Build Recipe Collection | 3 | 3
|  | Load Saved Recipe Data | 2.5 | 2
|  | Lock Recipe Edit Context | 2 | 2
Total
2026-08-12 | Wednesday | Set Up Android Cooking Forms | 1.5 | 1.5
|  | Build Recipe and Import UI | 2.5 | 2.5
|  | Add Input Validation | 2.5 | 2.5
Total
2026-08-13 | Thursday | Build Android Recipe Collection | 3 | 3
|  | Integrate Cooking API Calls | 1.5 | 1
|  | Run Cooking Unit Tests | 3 | 2
Total
2026-08-14 | Friday | Advisor Meeting 3 (present Cooking Implementation) | 1.5 | 1.5
|  | Present Cooking Implementation | 3 | 3
|  | Record Code Feedback | 2.5 | 1.5
Total
2026-08-15 | Saturday | Fix Recipe Import Feedback | 3 | 3
|  | Refine Web Cooking Flow | 2 | 1.5
|  | Refine Android Cooking Flow | 2 | 2
Total
2026-08-16 | Sunday | Run Recipe Regression Tests | 2 | 2
|  | Fix Cooking Failure States | 1.5 | 1.5
|  | Verify Recipe Permissions | 2.5 | 2.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Huang Qijun
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Optimize Recipe Creation Flow | 2.5 | 2.5
|  | Improve Cooking Accessibility | 2 | 2
|  | Polish Recipe UI Copy | 1.5 | 1.5
Total
2026-08-18 | Tuesday | Prepare Cooking Demo Recipes | 2.5 | 2.5
|  | Validate Cooking Full Stack | 2 | 2
|  | Update Cooking Test Evidence | 1.5 | 1.5
Total
2026-08-19 | Wednesday | DevSecOps Presentation (support) | 1 | 1
|  | Review Cooking Security Checks | 3 | 3
|  | Apply Cooking Report Feedback | 3 | 3
Total
2026-08-20 | Thursday | Rehearse Cooking Final Demo | 2.5 | 2.5
|  | Organize Cooking Submission | 2 | 2
|  | Prepare Cooking Fallbacks | 2 | 2.5
Total
2026-08-21 | Friday | AD Project Presentation (Cooking) | 2 | 2
|  | Run Final Preflight | 2.5 | 2.5
|  | Complete Report | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm