## Sprint 0
Project | FoodMind Application
Student | Lei Tianyou
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Project Briefing | 1.5 | 1.5
|  | Define Project Scope | 2.5 | 2.5
|  | Draft Proposal | 3.5 | 3
Total
2026-07-24 | Friday | Refine Proposal | 2 | 2
|  | Define MVP Scope | 2 | 2
|  | Review Proposal | 2.5 | 2.5
Total
2026-07-25 | Saturday | Analyze Target Users | 2.5 | 2.5
|  | Draft Use Cases | 2 | 2
|  | Map System Roles | 2 | 2
Total
2026-07-26 | Sunday | Consolidate Proposal | 2.5 | 2
|  | Review Architecture | 3.5 | 3
|  | Prepare Proposal Slides | 1.5 | 1.5
Total
2026-07-27 | Monday | Support Proposal Presentation | 1.5 | 1.5
|  | Rehearse Proposal | 3 | 3
|  | Record Feedback | 2.5 | 2.5
Total
2026-07-28 | Tuesday | Map Food Flow | 3.5 | 3
|  | Map Drink Flow | 2 | 2
|  | Map Group Food Flow | 2 | 2
Total
2026-07-29 | Wednesday | Review OpenAPI | 2 | 1.5
|  | Map Form Fields | 1.5 | 1.5
|  | Define Permissions | 3 | 3
Total
2026-07-30 | Thursday | Advisor Meeting 1 (support) | 1 | 1
|  | Confirm Task Split | 3.5 | 3.5
|  | Update Design Plan | 3 | 3
Total
2026-07-31 | Friday | Design Navigation | 2.5 | 2.5
|  | Design Type Picker | 1.5 | 1
|  | Review Accessibility | 2.5 | 2.5
Total
2026-08-01 | Saturday | Design Food Form | 3 | 3.5
|  | Define Rating Rules | 2 | 2
|  | Design Visibility | 2 | 2
Total
2026-08-02 | Sunday | Design Drink Form | 3 | 2
|  | Define Notes Rules | 2 | 2
|  | Design Photo Flow | 2.5 | 2.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Lei Tianyou
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | Design Group Food | 2 | 2
|  | Lock Group Context | 3 | 3
|  | Define Return Flow | 2 | 2
Total
2026-08-04 | Tuesday | Prototype Web Flow | 3 | 3
|  | Prototype Android Flow | 2 | 2
|  | Check Client Parity | 1.5 | 1.5
Total
2026-08-05 | Wednesday | Design Error States | 2 | 2
|  | Plan Draft Retention | 2.5 | 3.5
|  | Prevent Duplicates | 2.5 | 2.5
Total
2026-08-06 | Thursday | Run Usability Check | 2 | 2
|  | Refine Form Copy | 2.5 | 2
|  | Finalize Wireframes | 2 | 3
Total
2026-08-07 | Friday | Advisor Meeting 2 (support) | 1.5 | 1.5
|  | Present Design | 3 | 2.5
|  | Record Feedback | 3 | 3
Total
2026-08-08 | Saturday | Set Up Web Forms | 1.5 | 2
|  | Build Type Picker | 2.5 | 2.5
|  | Add Navigation | 3 | 2
Total
2026-08-09 | Sunday | Build Food Form | 2 | 2
|  | Add Validation | 3 | 4
|  | Map Rating Value | 2 | 1
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Lei Tianyou
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Build Drink Form | 1.5 | 1.5
|  | Add Photo Upload | 3.5 | 3.5
|  | Handle Visibility | 2.5 | 2.5
Total
2026-08-11 | Tuesday | Build Group Food | 3 | 3
|  | Load Group Names | 2.5 | 2.5
|  | Lock Group Selection | 1.5 | 1.5
Total
2026-08-12 | Wednesday | Set Up Android Forms | 1.5 | 1.5
|  | Build Food and Drink | 3 | 3
|  | Add Validation | 2.5 | 2.5
Total
2026-08-13 | Thursday | Build Android Group Food | 3 | 3
|  | Integrate API Calls | 1.5 | 1
|  | Run Code Tests | 3 | 2.5
Total
2026-08-14 | Friday | Advisor Meeting 3 (support) | 1 | 2
|  | Present Code | 3.5 | 3.5
|  | Record Code Feedback | 2.5 | 1.5
Total
2026-08-15 | Saturday | Fix Code Feedback | 3.5 | 3.5
|  | Refine Web Flow | 2 | 1.5
|  | Refine Android Flow | 2 | 2
Total
2026-08-16 | Sunday | Run Regression Tests | 3 | 3
|  | Fix Failure States | 1.5 | 1.5
|  | Verify Permissions | 2.5 | 2.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Lei Tianyou
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Optimize Form Flow | 2.5 | 2.5
|  | Improve Accessibility | 2 | 2
|  | Polish UI Copy | 2.5 | 2
Total
2026-08-18 | Tuesday | Prepare Demo Data | 2.5 | 2.5
|  | Validate Full Stack | 2 | 2
|  | Update Test Evidence | 2.5 | 2
Total
2026-08-19 | Wednesday | DevSecOps Presentation (support) | 1.5 | 1.5
|  | Review Security Checks | 3 | 3
|  | Apply Report Feedback | 3 | 3
Total
2026-08-20 | Thursday | Rehearse Final Demo | 3 | 3
|  | Organize Submission | 2.5 | 2
|  | Prepare Fallbacks | 1.5 | 1.5
Total
2026-08-21 | Friday | AD Project Presentation | 1.5 | 1.5
|  | Run Final Preflight | 3 | 3
|  | Complete Report | 2.5 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm