## Prioritised Product Backlog
P0 — Must have: essential to a secure, integrated recommendation product or to credible delivery evidence. P1 — Should have: significant user value after the P0 decision loop and platform foundation are viable.
Rank | ID | Priority | Product backlog item | Acceptance summary
1 | ARC-01 | P0 | Public API, security, and persistence foundation | Clients use only /api/v1; secrets, database access, and private-service credentials stay server-side.
2 | UC-01 | P0 | Register, sign in, and manage profile/preferences | Secure account and session handling; consistent preference validation on Web and Android.
3 | UC-02 | P0 | Create and manage food/drink records and history | Authorised CRUD with meal/place, price, rating, notes, media metadata, visibility, and consistent history.
4 | UC-03 | P0 | Trusted groups, group feed, and Want to Try | Only active members read group-visible content; group context is safe for recommendations.
5 | ARC-02 | P0 | Private agent and inference services | Schema-validated private services use allow-listed Backend tools and have no direct PostgreSQL access.
6 | ML-01 | P0 | Offline ML pipeline, evaluation, and model package | Reproducible UserCF, ItemCF, and LR package passes consumer-contract checks.
7 | UC-04 | P0 | Generate explainable ordered recommendations | Hard constraints and hybrid ranking return up to three ordered candidates and a clear lead result.
8 | UC-05 | P0 | Recommendation feedback loop | Accept, reject, later rating, and Would Eat Again are explicit, session-linked events.
9 | UX-01 | P0 | Recommendation-first Web home shell | The recommendation action is unmistakable in the first viewport across responsive widths.
10 | UX-02 | P0 | Recommendation-first Android home shell | Native navigation exposes the same modes and business destinations with Android accessibility conventions.
11 | QA-01 | P0 | Cross-client parity and contract integration | Equivalent inputs preserve permissions, validation, and metrics across clients.
12 | OPS-01 | P0 | CI/CD, cloud, security, and UAT evidence | Every demonstrated feature is tied to a reviewed revision, environment, test result, and owner evidence.
13 | DOC-01 | P0 | Documentation, scope governance, and delivery tracking | Claims remain evidence-backed and cross-repository changes are traceable.
14 | UX-03 | P1 | Permission-safe Explore | Every item retains its visibility rule; inaccessible content never appears.
15 | UC-06 | P1 | Generate a cooking plan | Return structured ingredients, steps, warnings, and a source recipe ID from controlled context.
16 | UC-07 | P1 | Search authorised platform content through Chatbot | Results include source references and preserve ownership and active-membership checks.
17 | UC-08 | P1 | Summarise and compare shared platform content | Output is grounded in source IDs and rejects inaccessible or unsupported claims.
18 | UC-09 | P1 | Personal dashboard and weekly recap | Web and Android show the same metric values with accessible text summaries.