## Committed Backlog
ID | Priority | Backlog item | Acceptance evidence | Reported result
S1-01 | P0 | Define the system boundary and public/private service architecture | Architecture, status, integration, and contract documentation identifies Spring Boot as the public API and agents as private services | Completed in reports
S1-02 | P0 | Freeze and reconcile public and internal contracts | Public OpenAPI baseline plus recommendation, cooking, chatbot, catalogue, and client-consumption notes | Completed in reports
S1-03 | P0 | Design account, session, preference, and permission behaviour | Refresh/CSRF design, preference model, ownership/group membership rules, and client error states | Completed in reports
S1-04 | P0 | Prototype recommendation-first Web and Android shells | Mode switch, recommendation context, result states, labelled navigation, and responsive/native layouts | Completed in reports
S1-05 | P0 | Design food/drink record and trusted-group flows | Record forms, type selection, validation, visibility, group feed, context selection, and return-state behaviour | Completed in reports
S1-06 | P0 | Design the explainable recommendation workflow | Candidate sources, hard filters, ranking handoff, reason codes, idempotency, fallback, and feedback concepts | Completed in reports
S1-07 | P1 | Prototype cooking workflows on both clients | Recipe collection, context, form validation, ingredient picker, generation, errors, and draft retention | Completed in reports
S1-08 | P1 | Prototype grounded chatbot history and source presentation | Session/history contracts, retry/idempotency behaviour, source reference cards, Web routes, and Android ViewModel/list | Completed in reports
S1-09 | P1 | Prototype dashboard and weekly recap | KPI cards, filters, grouping, formatting rules, responsive layout, and a real API-query approach | Completed in reports
S1-10 | P0 | Build and evaluate the first offline recommendation package | UserCF, ItemCF, LR training/evaluation, fixtures, manifest/checksum, model card, and runtime handoff | Completed in reports
S1-11 | P0 | Exercise cross-client and local integration assumptions | Shared validation/error behaviour, local stack use, and advisor-feedback revisions | Completed in reports
S1-12 | P0 | Maintain evidence-backed delivery documentation | Architecture, status, API/UX/ML traceability, and individual work records | Completed in reports

## Notes
Section | Content
Sprint goal | Define the cross-repository architecture and contracts, prove the recommendation-first user experience on Web and Android, and prepare implementation-ready designs for records, groups, recommendations, cooking, chatbot, dashboard, and the ML handoff.
Backlog relationships | S1-01 Architecture -> S1-02 Contracts; S1-01 -> S1-03 Security and permissions; S1-02 -> S1-04 Client shells; S1-02 -> S1-05 Records and groups; S1-03 -> S1-05; S1-05 -> S1-06 Recommendation design; S1-10 ML package -> S1-06; S1-02 -> S1-07 Cooking prototype; S1-02 -> S1-08 Chatbot prototype; S1-02 -> S1-09 Analytics prototype; S1-04 -> S1-11 Integration assumptions; S1-06/S1-07/S1-08/S1-09 -> S1-11; S1-01 -> S1-12 Delivery evidence; S1-11 -> S1-12.
Definition of done | A Sprint 1 item is marked completed only because one or more named member reports record the design, prototype, integration, test, or documentation work in the Sprint 1 period. The label does not assert that the later MVP was production-ready at that point.