## Committed Backlog
ID | Priority | Backlog item | Acceptance evidence | Reported result
S2-01 | P0 | Complete profile and food-preference behaviour on Web and Android | Dynamic cuisine chips, mutual exclusion, validation, Backend mapping, and client tests | Completed in reports
S2-02 | P0 | Deliver record, media, visibility, and group-food workflows | Food/drink/recipe forms, photo metadata, visibility, group use, permissions, and API integration | Completed in reports
S2-03 | P0 | Deliver the hybrid recommendation path | Personal/group/catalogue candidates, hard filters, agent delegation, inference package, reasons, diversity, fallback, and persistence | Completed in reports
S2-04 | P0 | Deliver recommendation feedback and re-recommendation behaviour | Accept/reject/reason/rating linkage, stable session identity, exclusions, diversity, and regression coverage | Completed in reports
S2-05 | P1 | Deliver cooking, recipe import, inventory, and shopping support | Structured forms, import/photo/visibility, generation, collection, API integration, permissions, and tests | Completed in reports
S2-06 | P1 | Deliver grounded chatbot workflows | Session/message persistence, natural-language routing, follow-up context, safety, source ordering, suggestions, and client UI | Completed in reports
S2-07 | P1 | Deliver dashboard and weekly recap | Backend-backed metrics, filters, chart series, cuisine/outcome views, Android/Web presentation, and regression tests | Completed in reports
S2-08 | P1 | Deliver permission-safe Explore and OneMap navigation | Authorised content, location search/details, Backend-owned routing, client map presentation, and secret handling | Completed in reports
S2-09 | P0 | Integrate versioned Backend/agent/inference/ML contracts | Consumer fixtures, model/version metadata, typed failures, release evidence, and compatibility gates | Completed in reports
S2-10 | P0 | Establish repository CI quality and security gates | Build/test/lint/contract/security workflows appropriate to each repository | Completed in reports
S2-11 | P0 | Establish integrated local and staging delivery | Compose validation/smoke, immutable image publication, staging deployment, DAST, and performance workflows | Completed in source and reports, subject to evidence limitations
S2-12 | P0 | Perform cross-client and real-stack regression work | Web scenarios, Android emulator coverage, permissions, integration fixes, and release/UAT records | Completed activities reported; not rerun in this documentation pass

## Notes
Section | Content
Sprint goal | Turn the Sprint 1 designs into an integrated MVP: complete user-facing Web and Android workflows, connect the Backend to private intelligence and offline ML artifacts, enforce permission and failure behaviour, and establish repeatable quality, security, integration, and staging-delivery controls.
Delivery dependency view | S2-09 Versioned contracts -> S2-03 Recommendation / S2-05 Cooking / S2-06 Chatbot; S2-01 Identity and preferences -> S2-03; S2-02 Records and groups -> S2-03 / S2-05 / S2-06; S2-03 -> S2-04 Feedback loop; S2-02 -> S2-07 Analytics; S2-04 -> S2-07; S2-02 -> S2-08 Explore and maps; S2-10 Repository gates -> S2-12 Cross-client regression; S2-03/S2-05/S2-06/S2-07/S2-08 -> S2-12; S2-12 -> S2-11 Local and staging delivery.
Definition of done (1) | "Completed in reports" means named Sprint 2 task rows describe implementation, integration, test, or documentation work.
Definition of done (2) | "Present in current source" means a corresponding controller, route/activity, migration, service, test, workflow, or deployment document was found in the 20 August source snapshot.
Definition of done (3) | Neither label alone means a production service was live or that this documentation pass reran the full test and deployment estate.