## Committed Backlog
ID | Priority | Backlog item | Acceptance evidence | Reported result
S3-01 | P0 | Polish and validate profile and food-preference flows on Web and Android | Repeat assigned flows; validate loading, error feedback and cross-client consistency; capture final demo evidence | Reported completed in Chen Chen's Sprint 3 report; screenshot evidence included
S3-02 | P0 | Complete the dashboard and Weekly Recap presentation | Cuisine, repeat and recommendation details; restored Would Eat Again Rate; real Web-to-API-to-database validation | Reported completed in Deng Yunke's Sprint 3 report
S3-03 | P0 | Polish recipe creation and cooking workflows | Recipe flow, accessibility and UI copy improvements; full-stack validation; demo recipes and updated evidence | Reported completed in Huang Qijun's Sprint 3 report; screenshot evidence included
S3-04 | P1 | Polish form flow, accessibility and UI copy | Demo data prepared; full-stack validation and test evidence updated; final demo rehearsed | Reported completed in Lei Tianyou's Sprint 3 report
S3-05 | P0 | Run chatbot release and regression verification | Android chat, recovery and idempotency; Backend/V22 and CI fixes; contract evidence; deployed-flow rehearsal and smoke test | Reported completed in Luo Yuxiang's Sprint 3 report
S3-06 | P0 | Prepare ML and inference reproducibility evidence | Repository and boundary review; inference features; model-package evaluation evidence; final reproducibility check and demo rehearsal | Reported completed in Wu Aomo's Sprint 3 report
S3-07 | P0 | Prepare and validate the Backend continuous-delivery pipeline | Pipeline built and exercised; Netty dependency correction; CI/CD results and failure follow-ups documented | Reported completed in Chen Yaqi's Sprint 3 report
S3-08 | P0 | Build and validate the Infra DevSecOps pipeline | Pipeline stages, delivery scripts, security evidence, deployment validation and cross-repository readiness review | Reported completed in Chen Yaqi's Sprint 3 report; deployment outcome remains workflow-specific
S3-09 | P1 | Normalise unsupported media uploads and image removal across Web and Android | Cross-client behaviour aligned and delivery readiness reviewed | Reported completed in Chen Yaqi's Sprint 3 report
S3-10 | P1 | Improve grounded Chat reference context and recent-place exploration | Richer source snippets in Backend Chat; Intelligence support for exploring recently recorded places; contract alignment review | Reported completed in Chen Yaqi's Sprint 3 report
S3-11 | P0 | Complete team-wide security review and DevSecOps presentation support | Feature-area security checks reviewed; feedback applied; Infra owner and feature owners prepared presentation evidence | Reported completed across the Sprint 3 reports
S3-12 | P0 | Complete final rehearsal, preflight, submission evidence and presentation | Feature demos rehearsed; fallbacks and screenshots organised; final preflight, presentation and individual reports completed | Reported completed across the Sprint 3 reports

## Notes
Section | Content
Sprint goal | Harden and present FoodMind as a cross-client, integrated product: polish core workflows, validate security and full-stack behaviour, prepare DevSecOps and reproducibility evidence, and complete the final demo and submission.
Delivery dependency view | S3-01/S3-02/S3-03/S3-04/S3-05/S3-06 feature readiness -> S3-11 security and DevSecOps evidence -> S3-12 final rehearsal and submission; S3-07 Backend CD and S3-08 Infra DevSecOps support the release path; S3-09/S3-10 are cross-client and grounded-experience refinements.
Definition of done (1) | "Reported completed" means the named Sprint 3 task rows have Actual hours populated in the member's source report. It is a report-derived statement, not an independent rerun of that work.
Definition of done (2) | "Screenshot evidence included" refers to repository-held screenshots from real local integration sessions documented on 11 and 15 August 2026. The screenshots show working features but do not prove every Sprint 3 backlog item.
Definition of done (3) | Source was inspected on 21 August 2026. Current repository presence, member reporting and older real-stack screenshots are kept as separate evidence types; no production-live claim is made.