## Sprint 0
Project | FoodMind Application
Student | Deng Yunke
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Attend Project Briefing | 2 | 2
|  | Review requirements; confirm Dashboard/Weekly Recap workstream | 2.5 | 2.5
|  | Team work allocation | 2 | 2
Total
2026-07-24 | Friday | Draft proposal | 2 | 2
|  | Analytics/OpenAPI baseline study | 2.5 | 2.5
|  | Architecture review | 2 | 2
Total
2026-07-25 | Saturday | Draft use cases | 2 | 2
|  | Map metric codes, units, dimensions and periods | 2.5 | 2.5
|  | Chart library research | 2 | 2
Total
2026-07-26 | Sunday | Consolidate proposal | 2 | 2
|  | Review architecture | 2.5 | 2.5
|  | Prepare proposal slides | 2 | 2
Total
2026-07-27 | Monday | Support Proposal Presentation | 2 | 2
|  | Rehearse | 2.5 | 2.5
|  | Record feedback | 2 | 2
Total
2026-07-28 | Tuesday | Web project setup | 2.5 | 2.5
|  | AnalyticsRoutes skeleton | 2 | 2
|  | React Query setup | 2 | 2
Total
2026-07-29 | Wednesday | Review analytics OpenAPI responses | 2 | 2
|  | Map MetricValue code/label/period/unit | 2.5 | 2.5
|  | Chart component skeleton | 2 | 2
Total
2026-07-30 | Thursday | Advisor Meeting 1 (support) | 1 | 1
|  | Dashboard layout design | 2.5 | 2.5
|  | Weekly recap layout design | 3 | 3
Total
2026-07-31 | Friday | Dashboard date filter design | 2 | 2
|  | Weekly summary card design | 2.5 | 2.5
|  | Accessibility review | 2 | 2
Total
2026-08-01 | Saturday | Analytics API client wiring | 2.5 | 2.5
|  | insight-metrics.ts | 2 | 2
|  | Metric formatting utils | 2 | 2
Total
2026-08-02 | Sunday | Chart series mapping | 2 | 2
|  | pivotByPeriod util | 2.5 | 2.5
|  | Design review | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Deng Yunke
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | Dashboard date filter implementation | 2.5 | 2.5
|  | Weekly KPI card layout | 2.5 | 2.5
|  | Loading/empty/error states | 2 | 2
Total
2026-08-04 | Tuesday | Dashboard URL params (from/to/groupBy) | 2.5 | 2.5
|  | React Query cache keys | 2 | 2
|  | Metric formatting (percentage/rating/currency) | 2 | 2
Total
2026-08-05 | Wednesday | Confirmed responsibility for the Dashboard and Weekly Recap workstream | 2 | 2
|  | Analysed the analytics user journey, date filters and weekly summaries | 2 | 2
|  | Located Web routes, metric utilities, API client and analytics modules | 2.5 | 2.5
Total
2026-08-06 | Thursday | Set up and ran the FoodMind infrastructure, backend and Web app locally | 2.5 | 2.5
|  | Reviewed Dashboard/Weekly Recap OpenAPI responses and metric fields | 2 | 2
|  | Confirmed integration boundaries; verified login and auth requests | 2 | 2
Total
2026-08-07 | Friday | Advisor Meeting 2 | 1.5 | 1.5
|  | Presented Dashboard layout, weekly-card design and backend-owned metrics | 2.5 | 2.5
|  | Recorded advisor feedback and updated the analytics plan | 2.5 | 2.5
Total
2026-08-08 | Saturday | Designed Dashboard date-range, group-by controls and six-week summary cards | 2 | 2
|  | Defined loading/error/retry/empty-data and real-zero display | 2 | 2
|  | Planned responsive chart spacing, labels, tooltips, legends and hierarchy | 2.5 | 2.5
Total
2026-08-09 | Sunday | Implemented Dashboard URL params (from/to/groupBy) with defaults | 2 | 2
|  | Connected the page to the authenticated API via the shared OpenAPI client | 2.5 | 2.5
|  | Added React Query cache keys; verified loading/retry/empty-range | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Deng Yunke
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Implemented filtering/formatting for rating, percentage, money and count | 2 | 2
|  | Built weekly KPI cards for rating, repeat purchase and recommendation rates | 2.5 | 2.5
|  | Ensured No-data vs real-zero display handling | 2 | 2
Total
2026-08-11 | Tuesday | Implemented period grouping and pivotByPeriod for chart series | 2.5 | 2.5
|  | Generated one summary-card group per returned week | 2 | 2
|  | Showed each week's top Repeat Frequency item and rate | 2 | 2
Total
2026-08-12 | Wednesday | Built Food and Drink Activity charts from backend period metrics | 2 | 2
|  | Built Spending by Currency (separate SGD/USD series, no conversion) | 2.5 | 2.5
|  | Built Cuisine Distribution and aggregated duplicate labels | 2 | 2
Total
2026-08-13 | Thursday | Built Recommendation Rates by Week with a fixed 0-100% scale | 2 | 2
|  | Built Recommendation Decision Details bar chart | 2.5 | 2.5
|  | Separated accepted candidate types from rejected reasons | 2 | 2
Total
2026-08-14 | Friday | Advisor Meeting 3 | 1 | 1
|  | Presented Dashboard charts, Weekly Recap and full-stack metric integration | 3 | 3
|  | Recorded code feedback; refined axes, legends, tooltips and spacing | 2.5 | 2.5
Total
2026-08-15 | Saturday | Created realistic six-week test records for the Dashboard demo | 2 | 2
|  | Added repeated orders, SGD/USD spending, cuisines and varied ratings | 2.5 | 2.5
|  | Added accepted/rejected outcomes and verified chart categories | 2 | 2
Total
2026-08-16 | Sunday | Ran Dashboard/Weekly Recap regression tests across the date range | 2 | 2
|  | Fixed duplicate Repeat Frequency cards and bar values | 2.5 | 2.5
|  | Fixed Weekly Recap weekStart validation (normalise to Monday) | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Deng Yunke
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Synced repositories and scanned the codebase; confirmed boundaries | 2 | 2
|  | Extended Weekly Recap with cuisine, repeat and recommendation detail | 2.5 | 2.5
|  | Polished UI copy; restored Recommendation Would Eat Again Rate | 2 | 2
Total
2026-08-18 | Tuesday | Prepared final Dashboard demo data and shared group evidence path | 2 | 2
|  | Validated the Web-to-API-to-database analytics flow (demo account) | 2.5 | 2.5
|  | Updated test evidence, screenshots, code references and Q&A prep | 2 | 2
Total
2026-08-19 | Wednesday | DevSecOps Presentation (support) | 1 | 1
|  | Review analytics security checks | 3 | 3
|  | Apply report feedback | 2.5 | 2.5
Total
2026-08-20 | Thursday | Rehearse Dashboard/Weekly Recap demo (Web + Android) | 3 | 3
|  | Organise submission evidence | 2 | 2
|  | Prepare fallbacks | 1.5 | 1.5
Total
2026-08-21 | Friday | AD Project Presentation (analytics) | 2 | 2
|  | Final preflight | 2 | 2
|  | Complete report | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm