## Sprint 0
Project | FoodMind Application
Student | Luo Yuxiang
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-24 | Friday | Baseline and scope analysis | 2 | 2
|  | Define chatbot responsibility | 2 | 2
|  | Map UI/API boundaries | 3 | 3
Total
2026-07-27 | Monday | Structured error handling (ChatRoute) | 2 | 2
|  | Write user-facing error copy | 2 | 2
|  | Add error mapping tests | 2 | 2
Total
2026-07-28 | Tuesday | Draft and recovery design | 2 | 2
|  | Design failed-message recovery | 2 | 2
|  | Verify restart and edit flow | 3 | 3
Total
2026-07-29 | Wednesday | Retry and source semantics | 2 | 2
|  | Define idempotency key behavior | 2 | 2
|  | Audit source scope handling | 2 | 2
Total
2026-07-30 | Thursday | Source selection experience | 2 | 2
|  | Add source search and preview | 2 | 2
|  | Fix explicit empty source scope | 3 | 3
Total
2026-07-31 | Friday | Guided chat UI | 2 | 2
|  | Add destination chips | 2 | 2
|  | Cover suggestion UI tests | 2 | 2
Total
2026-08-01 | Saturday | ChatSession/ChatMessage data model | 2 | 2
|  | ChatRoute enum mapping | 2 | 2
|  | ChatReference UI | 2 | 2
Total
2026-08-02 | Sunday | ChatDraftStore + recovery | 2 | 2
|  | Draft UI tests | 2 | 2
|  | Chat error/empty states | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Luo Yuxiang
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | Conversation history UX | 2 | 2
|  | Restore recent history | 2 | 2
|  | Align Android API snapshot | 3 | 3
Total
2026-08-04 | Tuesday | Network and contract alignment | 2 | 2
|  | Expose typed API errors | 2 | 2
|  | Verify contract and build wiring | 2 | 2
Total
2026-08-05 | Wednesday | Atomic chat transaction | 3 | 3
|  | Implement idempotency service | 2 | 2
|  | Validate agent result contract | 2 | 2
Total
2026-08-06 | Thursday | Backend retry handling | 2 | 2
|  | Replay completed idempotent result | 2 | 2
|  | Map backend failure responses | 2 | 2
Total
2026-08-07 | Friday | Recent conversation context | 3 | 3
|  | Build agent turn payload | 2 | 2
|  | Add context integration tests | 2 | 2
Total
2026-08-08 | Saturday | ChatRoutes Web page | 2.5 | 2.5
|  | feature/chat Android ViewModel | 2 | 2
|  | ChatList UI | 2 | 2
Total
2026-08-09 | Sunday | Grounded source references (UI) | 2 | 2
|  | Source reference cards | 2 | 2
|  | Chat smoke tests | 2.5 | 2.5
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Luo Yuxiang
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Suggestion persistence V22 | 2 | 2
|  | Persist suggestions and destinations | 2 | 2
|  | Verify history replay | 2 | 2
Total
2026-08-11 | Tuesday | Natural-language intent routing | 3 | 3
|  | Route search without rigid phrasing | 2 | 2
|  | Add routing contract cases | 2 | 2
Total
2026-08-12 | Wednesday | Clarification and follow-up | 2 | 2
|  | Use short follow-up context | 2 | 2
|  | Test underspecified prompts | 2 | 2
Total
2026-08-13 | Thursday | Safety and product boundaries | 3 | 3
|  | Redirect write-operation requests | 2 | 2
|  | Handle harmful-food questions safely | 2 | 2
Total
2026-08-14 | Friday | Grounded source responses | 2 | 2
|  | Prevent stale source leakage | 2 | 2
|  | Run agent regression tests | 2 | 2
Total
2026-08-15 | Saturday | Chat message source ordering | 2 | 2
|  | Grounding metadata UI | 2 | 2
|  | ChatRoute NAVIGATION handling | 2 | 2
Total
2026-08-16 | Sunday | Chatbot error/fallback states | 2 | 2
|  | Comparison and summary display | 2.5 | 2.5
|  | Chat E2E checks | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Luo Yuxiang
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Android verification (chat) | 3 | 3
|  | Verify recovery and idempotency | 2 | 2
|  | Run lint and debug build | 2 | 2
Total
2026-08-18 | Tuesday | Backend and V22 verification | 2 | 2
|  | Fix V22 test and CI failure | 2 | 2
|  | Review contract test evidence | 2 | 2
Total
2026-08-19 | Wednesday | Full-stack regression (chat) | 2 | 2
|  | Run Android and Backend gates | 2 | 2
|  | Rehearse deployed chatbot flow | 3 | 3
Total
2026-08-20 | Thursday | Delivery and reporting | 2 | 2
|  | Post-deployment smoke test | 2 | 2
|  | Prepare demo and contribution report | 2 | 2
Total
2026-08-21 | Friday | AD Project Presentation (chatbot) | 2 | 2
|  | Final chat preflight | 2 | 2
|  | Complete report | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm