## Sprint 0
Project | FoodMind Application
Student | Wu Aomo
Sprint Duration | 23/07/2026 - 02/08/2026
|  | Task | Plan | Actual
2026-07-23 | Thursday | Project briefing | 2 | 2
|  | ML repo review | 2 | 2.5
|  | Recommendation scope | 2.5 | 2.5
Total
2026-07-24 | Friday | Food record flow analysis | 2 | 2
|  | Candidate data model | 2 | 2
|  | Feature notes | 2.5 | 3
Total
2026-07-25 | Saturday | Data schema for training snapshot | 2.5 | 2.5
|  | Approved snapshot contract | 2 | 2
|  | Leakage/cold-start design notes | 2 | 2
Total
2026-07-26 | Sunday | Baseline and scope analysis | 2 | 2
|  | Define label semantics (accept/reject/passive) | 2.5 | 2.5
|  | Map UserCF/ItemCF boundaries | 2 | 2
Total
2026-07-27 | Monday | ML repo scope | 2 | 2.5
|  | API call chain (recommendation) | 2 | 2
|  | Architecture notes | 2.5 | 2.5
Total
2026-07-28 | Tuesday | Recommendation tables | 2 | 2
|  | Feedback signals | 2.5 | 2.5
|  | ER notes | 2 | 2.5
Total
2026-07-29 | Wednesday | Constraint filtering (hard rules stay in Backend) | 2.5 | 2.5
|  | Preference evidence | 2 | 2
|  | Model score notes | 2 | 2.5
Total
2026-07-30 | Thursday | Training snapshot format | 2.5 | 2.5
|  | HMAC pseudonymisation | 2 | 2
|  | Positive CF signal | 2.5 | 3
Total
2026-07-31 | Friday | Agent contract (recommendation-agent-v2) | 2 | 2
|  | Feature snapshot | 2.5 | 2.5
|  | Sprint summary | 2 | 2.5
Total
2026-08-01 | Saturday | prepare_foodcom.py data prep | 2.5 | 2.5
|  | merge_public_menus.py | 2 | 2
|  | Menu/catalogue seed data check | 2 | 2
Total
2026-08-02 | Sunday | build_collaborative_index.py skeleton | 2.5 | 2.5
|  | pipeline.py module layout | 2 | 2
|  | Unit test scaffolding | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 1
Project | FoodMind Application
Student | Wu Aomo
Sprint Duration | 03/08/2026 - 09/08/2026
|  | Task | Plan | Actual
2026-08-03 | Monday | ML pipeline (UserCF/ItemCF feature pipeline) | 2.5 | 2.5
|  | Feature engineering | 2 | 2.5
|  | Training notes | 2 | 2
Total
2026-08-04 | Tuesday | Data split | 2 | 2
|  | Model metrics (Top-1/Top-3) | 2.5 | 2.5
|  | Validation notes | 2 | 2.5
Total
2026-08-05 | Wednesday | UserCF review | 2.5 | 2.5
|  | ItemCF review | 2 | 2
|  | CF index notes | 2.5 | 3
Total
2026-08-06 | Thursday | Model packaging (manifest/checksum) | 2.5 | 2.5
|  | Manifest checks | 2 | 2
|  | Runtime handoff | 2.5 | 2.5
Total
2026-08-07 | Friday | Inference loading (runtime package) | 2.5 | 2.5
|  | Scoring vector | 2.5 | 2.5
|  | Frontend boundary | 2 | 3
Total
2026-08-08 | Saturday | train_hybrid_model.py (LR) | 3 | 3
|  | hybrid_lr_metrics.json | 2 | 2
|  | Model card | 2 | 2
Total
2026-08-09 | Sunday | build_runtime_package.py | 2.5 | 2.5
|  | SHA-256 checksums | 2 | 2
|  | Consumer fixture | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 2
Project | FoodMind Application
Student | Wu Aomo
Sprint Duration | 10/08/2026 - 16/08/2026
|  | Task | Plan | Actual
2026-08-10 | Monday | Web generate API (recommendation) | 2 | 2
|  | modelScore display contract | 2 | 2.5
|  | Frontend notes | 2.5 | 2.5
Total
2026-08-11 | Tuesday | Android request contract | 2 | 2
|  | API tests | 2 | 2
|  | Client summary | 2.5 | 3
Total
2026-08-12 | Wednesday | Group records features | 2 | 2.5
|  | Group SQL (evidence) | 2.5 | 2.5
|  | Group evidence | 2 | 2.5
Total
2026-08-13 | Thursday | Group features | 2 | 2
|  | Agent reasons | 2.5 | 2.5
|  | UserCF vs group | 2 | 2.5
Total
2026-08-14 | Friday | Selector policy | 2.5 | 2.5
|  | Recommendation types | 2 | 2.5
|  | PPT notes | 2.5 | 2.5
Total
2026-08-15 | Saturday | Reproduce experiments (seed/config) | 2.5 | 2.5
|  | Coverage/diversity evaluation | 2 | 2
|  | Limitations doc | 2 | 2
Total
2026-08-16 | Sunday | Freeze model version | 2.5 | 2.5
|  | Immutable model package | 2.5 | 2.5
|  | Consumer fixtures + model card | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm

## Sprint 3
Project | FoodMind Application
Student | Wu Aomo
Sprint Duration | 17/08/2026 - 23/08/2026
|  | Task | Plan | Actual
2026-08-17 | Monday | Repo sync | 2 | 2
|  | Latest code scan | 2.5 | 2.5
|  | ML boundary notes | 2 | 2.5
Total
2026-08-18 | Tuesday | Group evidence path | 2.5 | 2.5
|  | Inference features | 2 | 2.5
|  | Q&A prep | 2 | 2.5
Total
2026-08-19 | Wednesday | Code references | 2.5 | 2.5
|  | Code review discussion | 2 | 2
|  | Final review | 2 | 2.5
Total
2026-08-20 | Thursday | Rehearse ML demo (pipeline + model package) | 3 | 3
|  | Organise evaluation evidence | 2.5 | 2.5
|  | Prepare fallbacks | 1.5 | 1.5
Total
2026-08-21 | Friday | AD Project Presentation (ML) | 2 | 2
|  | Final model reproducibility check | 2.5 | 2.5
|  | Complete report | 2 | 2
Total
Note | Minimum 6.5 man-hours per day per person
Fill in the timesheet at the end of the day at 5pm