## Features
FoodMind — Feature Prioritisation | FoodMind — Feature Prioritisation | FoodMind — Feature Prioritisation | FoodMind — Feature Prioritisation | FoodMind — Feature Prioritisation | FoodMind — Feature Prioritisation
Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists. | Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists. | Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists. | Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists. | Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists. | Frozen MVP scope translated into implementation-ready features. Priority controls sequence, not whether an approved MVP feature exists.
ID | Feature / User Story | Priority | Owner(s) | Additional Details | Acceptance Outcome
UX-01 | Recommendation-first Web home shell | P0 | Chen Yaqi | Responsive React home with an Eat out & delivery / Cooking top switch, prominent Generate Recommendation action, Groups, Explore, Saved and profile destinations. | The lead recommendation action is unmistakable in the first viewport and the shell works at mobile, tablet and desktop widths.
UX-02 | Recommendation-first Android home shell | P0 | Member A / Member C | Native Android shell, mode switch, labelled bottom navigation, recommendation context and result-card states. Member A owns the foundation; Member C owns recommendation behaviour. | The native app exposes the same modes and business destinations as Web while following Android navigation and accessibility conventions.
UC-01 | Register, sign in and manage profile/preferences | P0 | Chen Yaqi / Member A | JWT-backed account, session, cuisine/spice/budget/dietary/location preferences and client validation parity. | A user can securely register, sign in, update preferences and recover from an expired session on Web and Android.
UC-02 | Create and manage food/drink records and history | P0 | Chen Yaqi / Member B | Create, edit, delete, filter and view records with meal/place, price, rating, notes, photo metadata, visibility and Would Eat Again. | Authorised users can manage their records and retrieve consistent daily, weekly and monthly history.
UC-03 | Trusted groups, group feed and Want to Try | P0 | Chen Yaqi / Member B | Create/join groups, membership and visibility checks, group feed, shared decision context, selected-result sharing and Want to Try. | Only active members can read Group-visible content, and group context can be used safely in recommendation requests.
UX-03 | Permission-safe Explore | P1 | Chen Yaqi / Member B | Image-led discovery surface composed only from authorised group-visible records and curated platform content; no public/follower feed or public internet search. | Every Explore item retains its source visibility rule and inaccessible content never appears.
UC-04 | Generate explainable ordered recommendations | P0 | Chen Yaqi / Wu Aomo / Member C | Hard constraints, UserCF, ItemCF and Logistic Regression produce up to three ordered Personal, Exploratory and Group-inspired candidates. | The client spotlights one lead result; Try another cycles the same response without creating a hidden new session.
UC-05 | Recommendation feedback loop | P0 | Chen Yaqi / Wu Aomo / Member C | Accept, reject with reason, re-recommend, later rating and Would Eat Again are stored as explicit events for analytics and offline learning. | Feedback is traceable to a session/candidate and passive non-selection is never treated as a negative label.
UC-06 | Generate a cooking plan | P1 | Huang Qijun / Member D | Independent Cooking Planner chain using manually entered or authorised pantry context, servings, time, budget, dietary rules and a controlled recipe catalogue. | Return structured ingredients, ordered steps, warnings and source recipe ID; no automatic inventory capture.
UC-07 | Search authorised platform content through Chatbot | P1 | Chen Yaqi / Member D | Chatbot Orchestrator routes search to the Platform Search Agent across authorised Meal Notes, Food Products and Places. | Results include source references and never bypass ownership or active group membership.
UC-08 | Summarise and compare shared platform content | P1 | Chen Yaqi / Member D | Content Summary Agent operates only on content explicitly shared into a Chatbot conversation and resolved through authorised backend tools. | Summaries/comparisons are grounded in source IDs and reject inaccessible or unsupported claims.
UC-09 | Personal dashboard and weekly recap | P1 | Chen Yaqi / Member C | Shared backend metric definitions for cuisine mix, spending trend, recommendation outcomes and periodic recap; Recharts on Web and Vico on Android. | Web and Android display the same metric values with accessible text summaries.
ARC-01 | Public API, security and persistence foundation | P0 | Chen Yaqi | Spring Boot /api/v1, Spring Security, JWT, JPA, PostgreSQL, ownership/group checks, validation and orchestration. | Clients use only the public API; secrets, database access and private service credentials remain server-side.
ARC-02 | Private Agent and runtime inference services | P0 | Chen Yaqi / Huang Qijun | Five-agent runtime plus a logically separate private inference service in foodmind-intelligence, with Pydantic contracts and service authentication. | Agents use allow-listed backend tools, cannot access PostgreSQL directly and return schema-validated grounded results.
ML-01 | Offline ML pipeline, evaluation and model package | P0 | Wu Aomo | Data validation, UserCF, ItemCF, LR training, time-aware evaluation, Top-1/Top-3 reporting and immutable model package with manifest/checksum. | A reproducible approved package passes consumer-contract tests before foodmind-intelligence loads it.
QA-01 | Cross-client parity and contract integration | P0 | Chen Yaqi / All members | Versioned public/internal contracts, Android-Web parity matrix, fixtures, permission/error states and end-to-end UC-01 to UC-09 checks. | The same inputs produce consistent permissions, validation and metrics across both clients.
OPS-01 | CI/CD, cloud, security and UAT evidence | P0 | Chen Yaqi / All members | Repository checks, container/dependency/secret scans, HTTPS cloud demonstration, OWASP ZAP, UAT evidence and final demo artefacts. | Every demonstrated feature is tied to a reviewed commit, environment, test result and owner evidence.
DOC-01 | Documentation, scope governance and delivery tracking | P0 | Chen Yaqi / All members | Formal Proposal/PPTX remain frozen; canonical guide, architecture/API/UX/ML documents, ownership and project status stay aligned. | No document claims implementation without repository evidence, and cross-repository changes are traceable through PRs.
Prioritisation Strategy | Prioritisation Strategy | Prioritisation Strategy | Prioritisation Strategy | Prioritisation Strategy | Prioritisation Strategy
Priority | Meaning | Application in FoodMind | Sequencing rule
P0 | Must — critical path | Recommendation-first vertical slice, trusted data/permissions, account/records/groups, feedback, ML/runtime foundation, integration and delivery assurance. | Start first; blocks the end-to-end demonstration or safe use of the product.
P1 | Should — approved secondary workflow | Cooking, Chatbot, Dashboard and Explore presentation remain in the frozen MVP but follow the P0 recommendation path and shared foundations. | Develop after its P0 contracts/foundations are stable; still required before final scope freeze.
P2 | Could — scope-safe polish | Accessibility refinement, visual polish and non-blocking usability improvements that do not add public feeds, ordering/payment or automatic inventory. | Only after P0/P1 acceptance criteria and integration evidence are secure.
D | Deferred — outside current MVP | Public internet restaurant search, ordering/payment, public/follower feeds, automatic inventory capture and advanced recommender models. | Do not implement without explicit scope approval and formal-source reconciliation.

## Business Process
FoodMind — Business Process | FoodMind — Business Process | FoodMind — Business Process | FoodMind — Business Process
Authorised decision flows for the recommendation-first experience, Cooking, Groups/Explore, Chatbot and analytics. | Authorised decision flows for the recommendation-first experience, Cooking, Groups/Explore, Chatbot and analytics. | Authorised decision flows for the recommendation-first experience, Cooking, Groups/Explore, Chatbot and analytics. | Authorised decision flows for the recommendation-first experience, Cooking, Groups/Explore, Chatbot and analytics.
Workflow | Actor / Component | Feature / Action | Outcome / Control
Eat out & delivery | User | Selects recommendation mode, optional trusted-group context and current budget/location/time constraints. | Generate Recommendation is the primary action; only authorised context is submitted.
Eat out & delivery | Spring Boot backend | Authenticates the user, resolves permissions/history/group context, retrieves candidates and applies hard constraints. | Invalid or inaccessible candidates are removed before model ranking.
Eat out & delivery | Recommendation Agent | Calls allow-listed rule/context tools and the private inference service, then applies diversity and verified reason codes. | Returns up to three ordered Personal, Exploratory and Group-inspired candidates.
Eat out & delivery | Web / Android | Spotlights the lead candidate and offers Try another without silently starting a new recommendation session. | Candidate rank, type, evidence and session identity remain intact.
Eat out & delivery | User | Accepts, rejects with reason, requests a re-recommendation or later rates the meal. | Explicit feedback is persisted; passive non-selection remains unknown.
Eat out & delivery | User / Group | Optionally shares the selected result back to the active trusted group. | Only active members can view the shared result.
Cooking | User | Switches to Cooking and enters ingredients/pantry context, servings, time, budget and dietary rules. | Inputs are manual or already authorised; no automatic inventory capture.
Cooking | Spring Boot backend | Validates request and calls the independent Cooking Planner Agent. | Cooking does not call the recommendation model or Chatbot workflow.
Cooking | Cooking Planner Agent | Matches controlled recipe catalogue entries and validates ingredient/time/budget/diet constraints. | Returns ingredients, ordered steps, warnings and source recipe ID.
Groups & Explore | User / Group owner | Creates or joins a trusted group and manages membership. | Membership status is the authority for Group-visible content.
Groups & Explore | User | Creates food records with Private or Group visibility and can save visible items as Want to Try. | Visibility is checked on every read, search, share and recommendation-context request.
Groups & Explore | Web / Android | Displays group feed and image-led Explore content from authorised group-visible and curated platform sources. | Explore is not a public/follower feed and performs no public internet search.
Chatbot | User | Starts a conversation and shares authorised Meal Note, Food Product or Place references. | Shared references preserve the original access rules.
Chatbot | Chatbot Orchestrator | Routes search intent to Platform Search Agent and summary/compare intent to Content Summary Agent. | Unsupported recommendation/cooking intents remain separate workflows.
Chatbot | Spring Boot tools | Resolve authorised content and return bounded structured sources. | Agents cannot query PostgreSQL directly or retrieve revoked content.
Analytics | Spring Boot backend | Aggregates shared metric definitions for cuisine, spend, recommendation outcomes and weekly recap. | The backend is the single source of metric truth.
Analytics | Web / Android | Renders accessible charts and text summaries in a dedicated Dashboard destination. | Dashboard remains in MVP but does not replace the recommendation-first home.
Delivery | Team | Runs contract, permission, UAT, security, CI/CD and cloud-demonstration checks. | A feature is complete only when it is buildable, demonstrable and evidenced.

## Technologies
FoodMind — Architecture-Centric Features | FoodMind — Architecture-Centric Features | FoodMind — Architecture-Centric Features | FoodMind — Architecture-Centric Features | FoodMind — Architecture-Centric Features
Implementation technologies, repository ownership and trust boundaries used to plan vertical slices. | Implementation technologies, repository ownership and trust boundaries used to plan vertical slices. | Implementation technologies, repository ownership and trust boundaries used to plan vertical slices. | Implementation technologies, repository ownership and trust boundaries used to plan vertical slices. | Implementation technologies, repository ownership and trust boundaries used to plan vertical slices.
Feature / Layer | Implementation Technologies | Repository | Owner | Architecture Notes
Responsive Web client | React, TypeScript, Vite; planned React Router, TanStack Query, Recharts and component/E2E testing | foodmind-web | Chen Yaqi | Consumes only HTTPS Spring Boot /api/v1; current recommendation-first UI is a prototype without backend integration.
Native Android client | Kotlin; current XML/AppCompat prototype; target Jetpack Compose, Navigation, ViewModel, StateFlow, Retrofit/OkHttp and Vico | foodmind-android | Members A–D | Uses the same business contracts as Web; no direct Agent, inference or database access.
Public API and orchestration | Java, Spring Boot, Spring Security, JWT, Bean Validation, Spring Data JPA, OpenAPI | foodmind-backend | Chen Yaqi | Authoritative boundary for authentication, permissions, validation, persistence, analytics and private-service calls.
Transactional data | PostgreSQL; JPA entities, migrations, indexes and permission-aware queries | foodmind-backend | Chen Yaqi | System of record for users, preferences, records, groups, recommendation sessions/feedback, cooking and chat metadata.
Optional media storage | S3-compatible object storage with server-issued references | foodmind-backend | Chen Yaqi | Optional for MVP record photos; clients never receive storage credentials.
Recommendation rules | Deterministic Java filtering, candidate retrieval, reason-code validation and diversity constraints | foodmind-backend | Chen Yaqi | Hard constraints and permissions run before ML; model predictions cannot override them.
Agent runtime | Python, FastAPI, Pydantic and bounded Agent graphs/tools | foodmind-intelligence | Chen Yaqi / Huang Qijun | Five agents: Recommendation, Cooking Planner, Chatbot Orchestrator, Platform Search and Content Summary.
Runtime inference | Private Python/FastAPI inference service, versioned feature schema, manifest/checksum validation | foodmind-intelligence | Chen Yaqi | Logically separate from Agents and offline training; may share an MVP deployment unit while preserving contracts.
Offline recommendation ML | Python, preprocessing, cosine-similarity UserCF/ItemCF, Logistic Regression, evaluation and packaging | foodmind-ml | Wu Aomo | Produces an immutable package; no production data, online retraining or runtime HTTP serving.
Cooking Planner | Controlled recipe catalogue, structured Pydantic request/response, ingredient/time/budget/diet validation | foodmind-intelligence | Huang Qijun | Independent end-to-end chain with explicit fallback and source recipe.
Chatbot search/summary | Agent routing plus allow-listed Spring Boot search/source-resolution tools | foodmind-intelligence / foodmind-backend | Chen Yaqi | Grounded in authorised platform content; no recommendation, cooking or public internet search.
Analytics presentation | Spring Boot aggregations, Recharts on Web, Vico on Android | backend / web / android | Chen Yaqi / Member C | Clients render backend-owned metrics and do not recalculate definitions independently.
Contracts and fixtures | OpenAPI public contracts, Pydantic internal schemas, JSON fixtures and model-package manifest | backend / intelligence / ml / docs | Chen Yaqi / Wu Aomo | Versioned producer-consumer boundaries prevent drift across six repositories.
CI/CD and security | GitHub Actions, build/test/lint, dependency/secret/container scans and OWASP ZAP | all repositories | Chen Yaqi / All members | A reviewed PR and evidence are required before integration or release.
Cloud demonstration | Docker, HTTPS, AWS-oriented application/database/object-storage deployment | backend / web / intelligence | Chen Yaqi | Private services and credentials remain off the public network; exact deployment must be documented before cloud completion.
Documentation and evidence | Markdown, formal DOCX/PPTX baselines, diagrams, status workbook, UAT/security reports and screenshots | foodmind-docs | Chen Yaqi / All members | Formal Proposal/PPTX stay unchanged; implementation claims require repository evidence.
Prototyping and Delivery Strategy | Prototyping and Delivery Strategy | Prototyping and Delivery Strategy | Prototyping and Delivery Strategy | Prototyping and Delivery Strategy
Stage | Focus | Exit evidence | Primary owners
1 — Demonstrate the interaction model | Recommendation-first Web/Android shells, two modes, dominant recommendation CTA, Groups and permission-safe Explore presentation. | Buildable mock/prototype, responsive/native screenshots and UX review. | Chen Yaqi; Members A–D
2 — Prove the P0 vertical slice | Account, preferences, records, groups, permissions, public API and deterministic recommendation fallback. | OpenAPI/fixtures, database migrations, client integration and permission tests. | Chen Yaqi; Members A–C
3 — Complete AI-supported workflows | Recommendation Agent + inference package, Cooking Planner, Chatbot and Dashboard. | Contract tests, Top-1/Top-3 evaluation, grounded sources, fallbacks and client flows. | Chen Yaqi; Huang Qijun; Wu Aomo; Members C–D
4 — Integrate and freeze | Android/Web parity, end-to-end tests, security, cloud demonstration, UAT and evidence. | Reviewed commits, CI results, deployment URL/environment, ZAP/UAT reports and demo script. | All members; coordinated by Chen Yaqi

## Project Status
FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report | FoodMind — Project Status Report
Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation. | Status date: 2026-07-28 ¦ Evidence-based assessment. C means a working, demonstrable artefact—not merely planned documentation.
ID | Feature | Technology / Repository | Owner | Priority | Requirements | Development | Integration Testing | Deployed to Cloud | Overall Progress | Evidence / Next Step
UX-01 | Recommendation-first Web home shell | React / foodmind-web | Chen Yaqi | P0 | C | C | N | N | 50% | Responsive two-mode prototype exists; next integrate routes, API, auth, charts and automated tests.
UX-02 | Recommendation-first Android home shell | Kotlin XML/AppCompat / foodmind-android | Member A / Member C | P0 | C | C | N | N | 50% | Native prototype exists; next migrate deliberately toward the target Compose architecture and backend integration.
UC-01 | Account, sign-in and preferences | Spring Security/JWT + React/Android | Chen Yaqi / Member A | P0 | C | N | N | N | 25% | Formal requirement is defined; implement public API, persistence, secure client sessions and parity tests.
UC-02 | Food/drink records and history | Spring REST/JPA/PostgreSQL + clients | Chen Yaqi / Member B | P0 | C | N | N | N | 25% | CRUD/history/visibility semantics are documented; no production backend or client feature flow yet.
UC-03 | Trusted groups, feed and Want to Try | Group APIs + Web/Android | Chen Yaqi / Member B | P0 | C | I | N | N | 37.5% | Web/Android prototypes show group context; implement membership, feed, visibility and Want to Try end to end.
UX-03 | Permission-safe Explore | Authorised group/search composition + clients | Chen Yaqi / Member B | P1 | C | I | N | N | 37.5% | Image-led prototype exists; implement backend source composition and negative permission tests.
UC-04 | Explainable ordered recommendations | Spring + Agents + UserCF/ItemCF/LR | Chen Yaqi / Wu Aomo / Member C | P0 | C | I | N | N | 37.5% | Lead-result interaction is prototyped; implement filtering, ranking, ordered candidates, reason codes and fallbacks.
UC-05 | Recommendation feedback loop | Feedback API/events + clients + ML data | Chen Yaqi / Wu Aomo / Member C | P0 | C | N | N | N | 25% | Implement session-linked accept/reject/recommend-again/rating events and supervised-label extraction.
UC-06 | Cooking plan | Cooking Planner Agent + Web/Android | Huang Qijun / Member D | P1 | C | N | N | N | 25% | Implement schema, controlled recipes, agent, fallback, backend route and both client flows.
UC-07 | Authorised Chatbot search | Chatbot/Search Agents + Spring tools | Chen Yaqi / Member D | P1 | C | N | N | N | 25% | Implement private runtime, bounded search tools, conversation UI and source-reference permission tests.
UC-08 | Chatbot summary and comparison | Summary Agent + source resolver | Chen Yaqi / Member D | P1 | C | N | N | N | 25% | Implement shared-reference resolver, grounded summary/compare output and revoked-access behaviour.
UC-09 | Dashboard and weekly recap | Spring aggregations + Recharts/Vico | Chen Yaqi / Member C | P1 | C | N | N | N | 25% | Implement metric definitions, aggregation endpoints, accessible charts and Web/Android parity.
ARC-01 | Public API, security and persistence | foodmind-backend | Chen Yaqi | P0 | I | N | N | N | 12.5% | Architecture conventions exist, but OpenAPI, modules, entities, security and runtime configuration are not implemented.
ARC-02 | Agent and runtime inference services | foodmind-intelligence | Chen Yaqi / Huang Qijun | P0 | C | N | N | N | 25% | Directory/design framework only; implement FastAPI apps, agent graphs, inference endpoint, model loader and tests.
ML-01 | Offline ML pipeline and model package | foodmind-ml | Wu Aomo | P0 | C | N | N | N | 25% | Design and release rules exist; implement data pipeline, CF features, LR training, evaluation, package and automation.
QA-01 | Cross-client parity and integration | all implementation repositories | Chen Yaqi / All members | P0 | I | N | N | N | 12.5% | Public/internal contracts, ERD, fixtures and UAT matrix must be created before end-to-end integration.
OPS-01 | CI/CD, cloud, security and UAT | GitHub Actions / Docker / cloud | Chen Yaqi / All members | P0 | I | N | N | N | 12.5% | Deployment runbooks, scans, cloud environment, ZAP and UAT evidence remain outstanding.
DOC-01 | Documentation and scope governance | foodmind-docs + repository docs | Chen Yaqi / All members | P0 | C | C | NA | NA | 100% | Formal baselines are preserved; canonical/product/architecture/API/UX/ML documents and ownership are aligned in reviewed PRs.
Status Legend and Formula Weights | Status Legend and Formula Weights | Status Legend and Formula Weights |  |  | Status Summary | Status Summary | Status Summary
C | Completed — demonstrable | 1 |  |  | KPI | Value | Interpretation
I | In Progress | 0.5 |  |  | Tracked features | 18 | All rows in the evidence-based status register
N | Not Started | 0 |  |  | Average overall progress | 31.94% | Formula-weighted across applicable stages
NA | Not Applicable | 0 |  |  | Requirements completed | 15 | Rows marked C in Requirements
[5 empty] | Development completed | 3 | Rows marked C in Development
[5 empty] | Integration completed | 0 | Rows marked C in Integration Testing
Status | Requirements | Development | Integration | Cloud
C | 15 | 3 | 0 | 0
I | 3 | 3 | 0 | 0
N | 0 | 12 | 17 | 17
NA | 0 | 0 | 1 | 1
Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules | Evidence Basis and Reporting Rules
Formal scope baseline: foodmind-docs/Team5_AD_Project_Proposal.docx (read-only).
Formal narrative/architecture baseline: foodmind-docs/FoodMind_Presentation_Proposal.pptx (read-only).
Approved clarification and ownership: FoodMind_AI_Project_Context_and_Tutoring_Guide.md and planning/team-work-allocation.md.
Implementation evidence: repository README status statements, file trees and Git history reviewed on 2026-07-28.
C requires a working feature ready for demonstration; I means tangible work exists but acceptance is incomplete; N means no implementation evidence; NA is excluded from the progress denominator.